## Sprint 1 Backlog
Story # | Sprint Backlog Item | Task # | Volunteer | Task Details | Initial Effort Estimate (hrs) | New Estimates of Effort remaining at end of |  |  | Status
[6 empty] | Day1 | Day2 | Day3
US001 | As a customer-account executive /cashier / teller I want to be able to log in the bank website with my user ID and password So that I carry out my transactions | Task 1 | Navya | Write a program for displaying the home page | 3 | 2 | 2 | 0 | Closed
|  | Task 2 | George | Design the UI for the Home page | 4 | 2 | 1 | 0 | Closed
|  | Task 3 | Jagadish | Design and create the DB fields | 2 | 1 | 0 | 0 | Closed
|  | Task 4 | Varshitha | Write test conditions to test the home page | 3 | 3 | 3 | 0 | Closed
|  | Task 5 | Ashwin | Integrate the code | 2 | 2 | 2 | 0 | Closed
US002 | As a customer-account executive I want to be able to capture new customer information So that I can create a new customer in the system | Task 1 | Navya | Write a code to display the new customer template | 3 | 3 | 1 | 0 | Closed
|  | Task 2 | George | Design the UI for the template | 5 | 5 | 4 | 0 | Closed
|  | Task 3 | Varshitha | Maintain the database and test for working | 5 | 3 | 2 | 0 | Closed
|  | Task 4 | Ashwin | Testing criterias planning and Testing | 4 | 2 | 0 | 0 | Closed
|  | Task 5 | Jagadish | Integrate the code | -- |  |  |  | closed
US003 | As a customer-account executive I want to be able to edit existing customer information So that I can store the updated customer information in the system | Task 1 | Navya | Write a code to edit customer details | 4 | 3 | 2 | 0 | Closed
|  | Task 2 | George | Design the UI for the template | 5 | 3 | 4 | 0 | Closed
|  | Task 3 | Varshitha | Maintain the database and test for working | 5 | 3 | 2 | 0 | Closed
|  | Task 4 | Ashwin | Testing criterias planning and Testing | 2 | 1 | 0 | 0 | Closed
|  | Task 5 | Jagadish | Integrate the code | 1 | 0 | 0 | 0 | closed
US004 | As a customer-account executive I want to be able to delete existing customer from system | Task 1 | Navya | Write a code to delete the customer | 3 | 3 | 1 | 0 | Closed
|  | Task 2 | George | Design the UI for the template | 5 | 5 | 4 | 0 | Closed
|  | Task 3 | Varshitha | Maintain the database and test for working | 5 | 3 | 2 | 0 | Closed
|  | Task 4 | Ashwin | Testing criterias planning and Testing | 4 | 2 | 0 | 0 | Closed
|  | Task 5 | Jagadish | Integrate the code | 2 | 1 | 0 | 0 | Closed
US005 | As a customer-account executive I want to be able to view the status of all the customers of the bank | Task 1 | Navya | Write a code to view the status of the customer | 3 | 2 | 1 | 0 | Closed
|  | Task 2 | George | Design the UI for the template | 4 | 4 | 2 | 0 | Closed
|  | Task 3 | Varshitha | Maintain the database and test for working | 4 | 2 | 2 | 0 | Closed
|  | Task 4 | Ashwin | Testing criterias planning and Testing | 4 | 2 | 0 | 0 | Closed
|  | Task 5 | Jagadish | Integrate the code | 1 | 1 | 0 | 0 | Closed
US006 | As a customer-account executive I want to be able to capture account details So that I can create a new bank account for an existing customer | Task 1 | Navya | Write a code to create a new account for existing customer | 5 | 4 | 1 | 0 | Closed
|  | Task 2 | George | Design the UI for the template | 5 | 5 | 4 | 0 | Closed
|  | Task 3 | Varshitha | Create database fields | 3 | 2 | 1 | 0 | Closed
|  | Task 4 | Ashwin | Testing criterias planning and Testing | 1 | 1 | 0 | 0 | Closed
|  | Task 5 | Jagadish | Integrate the code | 2 | 1 | 0 | 0 | Closed
US007 | As a customer-account executive I want to be able to delete an account of an existing customer | Task 1 | Navya | Write a code to delete account of existingcustomer | 3 | 3 | 1 | 0 | Closed
|  | Task 2 | George | Design the UI for the template | 5 | 5 | 4 | 0 | Closed
|  | Task 3 | Varshitha | Maintain the database and test for working | 5 | 3 | 2 | 0 | Closed
|  | Task 4 | Ashwin | Testing criterias planning and Testing | 4 | 2 | 0 | 0 | Closed
|  | Task 5 | Jagadish | Integrate the code | 1 | 1 | 0 | 0 | Closed
US008 | As a customer-account executive I want to be able to view the status of all the accounts of the bank | Task 1 | Navya | Write a code to view the status of all the accounts | 3 | 3 | 1 | 0 | Closed
|  | Task 2 | George | Design the UI for the template | 3 | 3 | 2 | 0 | Closed
|  | Task 3 | Varshitha | Maintain the database and test for working | 4 | 3 | 2 | 0 | Closed
|  | Task 4 | Ashwin | Testing criterias planning and Testing | 2 | 0 | 1 | 0 | Closed
|  | Task 5 | Jagadish | Integrate the code | 1 | 1 | 0 | 0 | Closed
US009 | As a customer-account executive I want to be able to search for a customer So that I am able to view the details | Task 1 | Navya | Write a code to search for a customer | 3 | 3 | 1 | 0 | Closed
|  | Task 2 | George | Design the UI for the template | 4 | 1 | 0 | 0 | Closed
|  | Task 3 | Varshitha | Create database fields | 5 | 3 | 2 | 0 | Closed
|  | Task 4 | Ashwin | Testing criterias planning and Testing | 1 | 0 | 1 | 0 | Closed
|  | Task 5 | Jagadish | Integrate the code | 1 | 0 | 1 | 0 | Closed
US0010 | As a Cashier/ Teller I want to be able to search for a bank account So that I am able to view the details | Task 1 | Navya | Write a code to search | 3 | 3 | 1 | 4 | Closed
|  | Task 2 | George | Design the UI for the template | 5 | 5 | 4 |  | Closed
|  | Task 3 | Varshitha | Create database fields | 5 | 3 | 2 | 0 | Closed
|  | Task 4 | Ashwin | Testing criterias planning and Testing | 4 | 2 | 0 | 1 | Closed
|  | Task 5 | Jagadish | Integrate the code | 3 | 2 | 1 | 0 | Closed
US0011 | As a Cashier/ Teller I want to be able to deposit money into a customer's account So that I am able to service the customer's request | Task 1 | Navya | Write a code to serve the customer request | 3 | 3 | 1 | 0 | Closed
|  | Task 2 | George | Design the UI for the template | 5 | 5 | 4 | 0 | Closed
|  | Task 3 | Varshitha | Create database fields | 5 | 3 | 2 | 0 | Closed
|  | Task 4 | Ashwin | Testing criterias planning and Testing | 4 | 2 | 0 | 0 | Closed
|  | Task 5 | Jagadish | Integrate the code | 1 | 0 | 0 | 1 | Closed
US0012 | As a Cashier/ Teller I want to be able to withdraw money from a customer's account So that I am able to service the customer's request | Task 1 | Navya | Write a code to withdraw money | 3 | 3 | 0 | 0 | Closed
|  | Task 2 | George | Design the UI for the template | 2 | 1 | 4 | 0 | Closed
|  | Task 3 | Varshitha | Maintain the database and test for working | 5 | 3 | 2 | 0 | Closed
|  | Task 4 | Ashwin | Testing criterias planning and Testing | 4 | 2 | 0 | 0 | Closed
|  | Task 5 | Jagadish | Integrate the code | 1 | 0 | 1 | 0 | Closed
US0013 | As a Cashier/ Teller I want to be able to transfer money from a customer's account So that I am able to service the customer's request | Task 1 | Navya | Write a code to transfer the money | 2 | 1 | 1 | 0 | Closed
|  | Task 2 | George | Design the UI for the template | 3 | 2 | 1 | 0 | Closed
|  | Task 3 | Varshitha | Maintain the database and test for working | 5 | 3 | 2 | 0 | Closed
|  | Task 4 | Ashwin | Testing criterias planning and Testing | 4 | 2 | 0 | 0 | Closed
|  | Task 5 | Jagadish | Integrate the code | 1 | 0 | 1 | 0 | Closed
US0014 | As a Cashier/ Teller I want to be able to print an account statement So that I am able to service the customer's request | Task 1 | Navya | Write a code to display the new customer template | 3 | 3 | 1 | 0 | Closed
|  | Task 2 | George | Design the UI for the template | 5 | 5 | 4 | 0 | Closed
|  | Task 3 | Varshitha | Maintain the database and test for working | 5 | 3 | 2 | 0 | Closed
|  | Task 4 | Ashwin | Testing criterias planning and Testing | 4 | 2 | 0 | 0 | Closed
|  | Task 5 | Jagadish | Integrate the code | 1 | 0 | 0 | 1 | Closed

## Sprint 1 Burndown Chart
Day0 | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
300 | 260 | 220 | 160 | 90 | 65 | 0
300 | 250 | 200 | 150 | 100 | 50 | 0