## sprint1 Backlog
Story # | Sprint Backlog Item | Task # | Volunteer | Task Details | Initial Effort Estimate (hrs) | New Estimates of Effort remaining at end of | [5 empty] | Status
[6 empty] | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
US001 | As a admission desk executive /pharmacist/ diagnostic center executive I want to be able to log in the hospital website with my user ID and password So that I carry out my transactions | Task 1 | Navya | Write a program for displaying the home page | 3 | 2 | 1 | 1 | 0 | 0 | 0 | Closed
|  | Task 2 | George | Write a program for displaying the home page | 4 | 2 | 1 | 1 | 0 | 0 | 0 | Closed
|  | Task 3 | Maduvanti | Design and create the DB fields | 2 | 1 | 1 | 1 | 0 | 0 | 0 | closed
|  | Task 4 | Jagadish | Design and create the DB fields | 2 | 1 | 0 | 0 | 1 | 0 | 0 | Closed
|  | Task 5 | Varshitha | Write test conditions to test the home page | 3 | 3 | 2 | 0 | 1 | 1 | 0 | Closed
|  | Task 6 | Ashwin | Integrate the code | 2 | 2 | 2 | 0 | 1 | 0 | 0 | Closed
US002 | As a admission desk executive I want to be able to capture new patient information So that I can create a new patient in the system | Task 1 | Navya | Write a code to capture the new patient information | 3 | 2 | 1 | 1 | 0 | 1 | 0 | Closed
|  | Task 2 | George | Design the UI for the template | 5 | 3 | 3 | 2 | 0 | 1 | 0 | Closed
|  | Task 3 | Maduvanti | Maintain the database and test for working | 5 | 3 | 2 | 2 | 0 | 1 | 0 | Closed
|  | Task 4 | Ashwin | Testing criterias planning and Testing | 4 | 2 | 0 | 3 | 0 | 0 | 0 | Closed
|  | Task 5 | Jagadish | Integrate the code | 2 | 0 | 0 | 0 | 0 | 0 | 1 | Closed
US003 | As a admission desk executive I want to be able to edit existing patient information So that I can store the updated patient information in the system | Task 1 | Navya | Write a code to edit patient details | 4 | 3 | 2 | 0 | 0 | 0 | 0 | Closed
|  | Task 2 | George | Design the UI for the template | 5 | 3 | 4 | 0 | 0 | 0 | 0 | Closed
|  | Task 3 | Varshitha | Maintain the database and test for working | 5 | 3 | 2 | 2 | 2 | 0 | 0 | Closed
|  | Task 4 | Maduvanti | Testing criterias planning and Testing | 2 | 1 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 5 | Jagadish | Integrate the code | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Closed
US004 | As a admission desk executive I want to be able to delete existing patient from system | Task 1 | Navya | Write a code to delete the exsisting patient | 3 | 3 | 1 | 2 | 0 | 0 | 0 | Closed
|  | Task 2 | George | Design the UI for the template | 5 | 5 | 4 | 2 | 0 | 0 | 0 | Closed
|  | Task 3 | Varshitha | Maintain the database and test for working | 5 | 3 | 2 | 0 | 0 | 0 | 0 | Closed
|  | Task 4 | Maduvanti | Testing criterias planning and Testing | 4 | 2 | 0 | 0 | 2 | 0 | 0 | Closed
|  | Task 5 | Ashwin | Integrate the code | 2 | 1 | 0 | 1 | 0 | 0 | 0 | Closed
US005 | As a admission desk executive I want to be able to view all the active patients currently admitted in the hospital | Task 1 | Navya | Write a code to view aill the active patient | 3 | 2 | 1 | 0 | 0 | 0 | 0 | Closed
|  | Task 2 | Maduvanti | Design the UI for the template | 4 | 4 | 1 | 2 | 1 | 3 | 0 | Closed
|  | Task 3 | Varshitha | Maintain the database and test for working | 4 | 1 | 2 | 2 | 0 | 0 | 0 | Closed
|  | Task 4 | Ashwin | Testing criterias planning and Testing | 4 | 2 | 0 | 0 | 0 | 1 | 0 | Closed
|  | Task 5 | Jagadish | Integrate the code | 1 | 1 | 0 | 1 | 2 | 0 | 0 | Closed
US006 | As a admission desk executive I want to be able to search for a patient So that I am able to view the details | Task 1 | Maduvanti | Write a code to search for a existing patient | 5 | 4 | 1 | 0 | 0 | 0 | 0 | Closed
|  | Task 2 | George | Design the UI for the template | 5 | 5 | 4 | 2 | 0 | 0 | 0 | Closed
|  | Task 3 | Varshitha | Create database fields | 3 | 2 | 1 | 0 | 0 | 0 | 0 | Closed
|  | Task 4 | Ashwin | Testing criterias planning and Testing | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Closed
|  | Task 5 | Jagadish | Integrate the code | 2 | 1 | 0 | 0 | 0 | 0 | 0 | Closed
US007 | As a pharmacist I want to be able to capture the medicines issued to a patient So that I can issue new medicines for an existing patient | Task 1 | Navya | Write a code to capture medicine details of existing patient | 3 | 3 | 1 | 0 | 2 | 0 | 0 | Closed
|  | Task 2 | George | Design the UI for the template | 5 | 5 | 4 | 1 | 2 | 0 | 0 | Closed
|  | Task 3 | Maduvanti | Maintain the database and test for working | 5 | 3 | 2 | 0 | 0 | 0 | 0 | Closed
|  | Task 4 | Ashwin | Testing criterias planning and Testing | 4 | 2 | 0 | 0 | 0 | 2 | 0 | Closed
|  | Task 5 | Jagadish | Integrate the code | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Closed
US008 | As a diagnostics executive I want to be able to capture the diagnostocs conducted to a patient So that I can add new tests for an existing patient | Task 1 | Navya | Write a code to view the status of diagnostics conducted | 3 | 3 | 1 | 2 | 0 | 0 | 0 | Closed
|  | Task 2 | George | Design the UI for the template | 3 | 3 | 2 | 0 | 0 | 1 | 0 | Closed
|  | Task 3 | Varshitha | Maintain the database and test for working | 4 | 3 | 2 | 2 | 0 | 0 | 0 | Closed
|  | Task 4 | Ashwin | Testing criterias planning and Testing | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Closed
|  | Task 5 | Jagadish | Integrate the code | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Closed
US009 | As a admission desk executive I want to be able to get existing patient information So that I can raise the bill for the patient | Task 1 | Navya | Write a code to search for a exsiting patient information to generate bill | 3 | 3 | 1 | 0 | 0 | 0 | 0 | Closed
|  | Task 2 | George | Design the UI for the template | 4 | 1 | 0 | 0 | 2 | 0 | 0 | Closed
|  | Task 3 | Varshitha | Create database fields | 5 | 3 | 2 | 0 | 2 | 0 | 0 | Closed
|  | Task 4 | Ashwin | Testing criterias planning and Testing | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Closed
|  | Task 5 | Jagadish | Integrate the code | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Closed
|  |  |  | Total | 148 | 99 | 56 | 30 | 18 | 11 | 1

## sprint1 Burndown chart
Day0 | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
148 | 99 | 56 | 30 | 18 | 11 | 1
148 | 90 | 50 | 30 | 14 | 9 | 0